## Sheet1
Time Estimates
Non-Game Work
Writing and Art |  | Segmentation introduction
itemize
Dialogue/exposition writing |  | Dialogue/exposition writing
Game introduction | 2
Networking overview | 2
Checksum introduction | 2
Routing introduction | 2
Segmentation introduction | 2
Miscellaneous dialogue | 2
Character design
Instructor 1 art | 5
Instructor 2 art | 5
Instructor 3 art | 5
Mini-game art
Checksum game
Binary background art | 3
Check button icon art | 3
Routing game
Post office icon design | 3
Map design | 3
Segmentation game
Background layout | 3
Package design | 3
General Programming
Main menu
Game selection buttons | 2
Layout decisions | 2
Settings button | 2
Level selection
Level selection buttons | 2
Level selection recyclerview | 4
General buttons | 2
Settings menu
Instructor switch | 2
Music toggle | 2
Sound effects toggle | 2
Google Play account connectivity | 2
Loading screen | 2
Leaderboard
Get points from games | 2
Player recyclerview | 4
Top 3 designation | 2
Sharing button | 2
Header | 2
Google Play connection | 4
Monthly Leaderboard submission | 2
Weekly Leaderboard submission | 2
Daily Leaderboard submission | 2
Learning Games
Checksum Game
Animation of incoming numbers | 3
Textviews for numbers | 2
Buttons for input | 2
General design | 2
Random sum generation | 2
Checksum validation | 2
Points assignment | 2
Add score to total | 2
Transition animations | 3
Routing Game
Line weight textviews | 2
Router textviews | 2
Buttons to allow for selection | 2
Transition animations | 3
Backend
Random path generation | 2
Random path weight generation | 2
Best path calculation | 2
Points assignment | 2
Add score to total | 2
Best path verification | 2
Segmentation Game
Animation of boxes | 4
Buttons for packages | 2
Transition animations | 3
Backend
Job randomization | 2
Package generation/randomization | 2
Game timer | 2
Points assignment | 2
Add score to total | 2
Totals
Non-Game Work
Writing and Art: 45 hours
General Programming: 46 hours
Subtotal: 91 hours
Learning Games
Checksum Game: 20 hours
Routing Game: 21 hours
Segmentation Game: 19 hours
Subtotal: 60 hours

## Sheet2
update leaderboard
segmentation game backend
dijkstra backend
checksum backend
segmentation front end
checksum front end
path find front end
connect leaderboard to Google Play
Connection screens (between games)
level selection menu
| Week | 1 | 2 | 3 | 4
| Teaching dialog | 3 | 3 | 3 | 2
| Character design (finesse) | 2 | 2 | 2 | 2
| Home menu | 7 | 7 | 7 | 4
|  | 12 | 12 | 12 | 8
| week | 1 | 2 | 3
[5 empty] | Week | 1 | 2 | 3 | 4
[5 empty] | Home menu | 6 | 2 | 0 | 0
[5 empty] | Graphics/Visuals | 5 | 4 | 2 | 0
[5 empty] | Checksum front end | 25 | 20 | 20 | 4
[5 empty] | Checksum back end | 12 | 10 | 6 | 0
[5 empty] | Settings menu | 5 | 2 | 0 | 0
[5 empty] | Pause menu | 5 | 3 | 0 | 0
[6 empty] | 58 | 41 | 28 | 4
[5 empty] | Week | 1 | 2 | 3 | 4
[5 empty] | Graphics/Visuals | 5 | 5 | 4 | 0
[5 empty] | pathfind front end | 30 | 30 | 25 | 2
[5 empty] | pathfind back end | 6 | 6 | 5 | 4
[5 empty] | sprint 1 testing | 15 | 15 | 15 | 15
[5 empty] | dialog writing | 10 | 10 | 4 | 4
[6 empty] | 66 | 66 | 53 | 25
[5 empty] | Week | 0 | 1 | 2 | 3
[5 empty] | pathfind front end | 3 | 3 | 0
[5 empty] | pathfind back end | 8 | 5 | 4
[5 empty] | sprint 1 and 2 testing | 10 | 10 | 8
[5 empty] | Graphics and Visuals | 2 | 1 | 0
[5 empty] | dialog writing | 5 | 5 | 5
[5 empty] | Checksum level integration | 1 | 1 | 1
[5 empty] | Checksum game termination | 1 | 1 | 1
[5 empty] | Segmentation front end | 20 | 20 | 15
[5 empty] | Segmentation back end | 8 | 8 | 4
[5 empty] | Checksum front end move numbers | 2 | 2 | 1
[5 empty] | Changing resolution and doing Android/mobile switch | 3 | 3 | 2
[6 empty] | 63 | 59 | 41